AUEVIA

The Global Network for Medical Students

7-Day MVP Launch Plan

Budget: $200–$500  |  Target: Medical Students  |  Launch: April 3, 2026

# The Vision

Auevia is the IEEE of medicine — a professional network that gives medical students identity, community, credentials, and career acceleration. While IEEE serves 400,000+ engineers worldwide through chapters, publications, conferences, and certifications, medical students have no equivalent. Auevia fills that gap.

The MVP isn’t about building everything. It’s about proving demand and creating a magnet that pulls in your first 100 founding members. Everything else grows from there.

# What “Live” Looks Like on Day 7

| Feature | Description |
| --- | --- |
| Public Website | Clean landing page explaining Auevia’s mission, value proposition, and sign-up flow. |
| Member Registration | Students can create an account with name, medical school, year, and interests. |
| Member Dashboard | A simple profile page showing their membership status, chapter, and upcoming events. |
| Chapter Directory | A page listing founding chapters (even if it’s just 2–3 to start). |
| Events/Resources Feed | A curated feed of workshops, articles, or resources — even if manually populated. |
| Community Space | A Discord server or built-in forum where members can connect. |
| Social Presence | Instagram + LinkedIn accounts actively posting and building hype. |

# Recommended Tech Stack

With a $200–$500 budget and 7 days, we need tools that are fast to deploy, free or cheap, and don’t require custom backend development. Here’s the stack:

| Component | Tool | Cost | Why |
| --- | --- | --- | --- |
| Website + Member Portal | Next.js on Vercel (free tier) | $0 | Best balance of speed, customization, and free hosting. Alternatively: Framer or Carrd ($19) for a simpler landing page. |
| Authentication | Clerk or Supabase Auth (free tier) | $0 | Handles sign-up, login, profiles out of the box. No custom auth code needed. |
| Database | Supabase (free tier) | $0 | PostgreSQL database with 500MB free. Stores member profiles, chapters, events. |
| Community | Discord (free) | $0 | Instant community space. Create channels per chapter, topic, and year. |
| Domain | auevia.org or auevia.com | $12–15 | Use Namecheap or Cloudflare Registrar. |
| Email | Resend or Mailgun (free tier) | $0 | Welcome emails, event notifications. Free up to 100 emails/day. |
| Design | Canva Pro (free trial) + AI tools | $0 | Logo, social templates, brand kit. |
| Social Media | Instagram + LinkedIn | $0 | Primary channels for medical student audience. |
| Merch (Phase 2) | Printful / Printify | $0 upfront | Print-on-demand. No inventory risk. Launch after member base exists. |
| Analytics | Vercel Analytics + Plausible (free) | $0 | Track sign-ups, engagement, and traffic sources. |

Estimated Total: $12–$50 for MVP

Remaining budget ($150–$450) reserved for: social media ads for launch, merch samples, and contingency.

# 7-Day Sprint: Day-by-Day Breakdown

## Day 1 — Foundation (Friday, March 27)

### Brand Identity

Define brand: name (Auevia), tagline (“The Global Network for Medical Students”), mission statement (2–3 sentences).

Create logo using Canva or AI tools (Midjourney, DALL-E). Keep it clean and medical-professional.

Choose brand colors: primary (deep teal #0D4772), secondary (sky blue #1A73A7), accent (gold #D4A843).

Create brand kit in Canva: logo variants, color codes, font pairing (e.g., Inter + Playfair Display).

### Digital Setup

Register domain (auevia.org recommended — .org signals nonprofit/community).

Create GitHub repo for the website.

Set up Vercel account and connect to repo.

Create Supabase project (database + auth).

Create Discord server with initial channel structure: #welcome, #introductions, #general, #events, #resources, #chapter-leads.

### Social Media

Create Instagram account (@auevia.global or @auevia.med).

Create LinkedIn page.

Design 5 pre-launch teaser posts using Canva templates.

## Day 2 — Website Build (Saturday, March 28)

### Landing Page

Hero section: mission statement + “Join as Founding Member” CTA.

What is Auevia section: 3–4 value pillars (Community, Knowledge, Credentials, Career).

How it works: simple 3-step visual (Sign Up → Join Chapter → Grow).

Founding member perks section (early access, leadership roles, free merch, networking).

FAQ section.

Footer with social links and contact email.

### Auth Flow

Integrate Clerk or Supabase Auth.

Sign-up form: name, email, medical school, year (pre-clinical/clinical/intern), interests.

Email verification.

Basic profile page after login.

## Day 3 — Member Portal (Sunday, March 29)

### Dashboard

Member dashboard: welcome message, profile summary, membership badge.

Chapter directory page (start with 2–3 seed chapters based on your network).

Events/resources feed — can be a simple list that you manually update via Supabase.

Member directory (opt-in): name, school, year, interests. Helps members find each other.

### Database Schema

Users table: id, name, email, school, year, chapter_id, role, created_at.

Chapters table: id, name, location, description, lead_user_id.

Events table: id, title, description, date, chapter_id, link.

Resources table: id, title, type, url, created_at.

## Day 4 — Content & Community (Monday, March 30)

### Content Creation

Write 3–5 foundational resources/articles: “What is Auevia?”, “How to Start a Chapter”, “10 Skills Every Medical Student Needs Beyond Textbooks”.

Create a Chapter Starter Kit (Google Doc or PDF): guidelines, branding assets, event ideas, roles template.

Record a 60-second intro video for social media (phone is fine — authenticity > production value).

### Discord Setup

Write welcome bot message with rules and role selection.

Create role-based channels: by year, by interest (research, clinical skills, leadership).

Pin introductory resources in #welcome.

Invite 5–10 trusted friends/peers as “founding members” to seed conversations.

## Day 5 — Polish & Test (Tuesday, March 31)

### QA & Refinement

Test full sign-up flow end to end (desktop + mobile).

Fix responsive design issues.

Test email delivery (welcome email, verification).

Review all copy for typos, unclear messaging.

Optimize page load speed (images, lazy loading).

### SEO & Metadata

Add meta tags, Open Graph tags for social sharing.

Create a compelling og:image (the preview when someone shares your link).

Set up Google Analytics or Plausible.

Submit sitemap to Google Search Console.

## Day 6 — Pre-Launch Buzz (Wednesday, April 1)

### Outreach

Post teaser on Instagram: “Something big is coming for medical students.”

Share on LinkedIn with a personal story about why you’re building this.

DM 20–30 medical students you know personally. Ask them to sign up on launch day.

Reach out to 3–5 medical student organizations or group chats and offer to present Auevia.

Post in relevant Reddit communities (r/medicalschool, r/premed) — be genuine, not spammy.

### Launch Assets

Create launch announcement graphic.

Write launch email/message for your network.

Prepare an Instagram Story series (5–7 slides) explaining Auevia.

Draft a Twitter/X thread if relevant to your audience.

## Day 7 — LAUNCH (Thursday, April 2)

### Go Live

Push final code to production.

Post launch announcement on Instagram, LinkedIn, Twitter/X.

Send launch message to your personal network and DM list.

Share Discord invite link publicly.

Monitor sign-ups in real-time via Supabase dashboard.

### Day-of Tasks

Respond to every new member personally (even a quick “Welcome!” DM).

Post a welcome thread in Discord tagging new members.

Fix any bugs that surface immediately.

Screenshot and share sign-up milestones on social (“10 founding members!”, “25!”, “50!”).

Celebrate. You just launched a global medical student network from zero in 7 days.

# Budget Breakdown

| Item | Cost | When |
| --- | --- | --- |
| Domain registration | $12–15 | Day 1 |
| Vercel hosting | $0 (free tier) | Day 1 |
| Supabase | $0 (free tier) | Day 1 |
| Clerk Auth | $0 (free tier, up to 10K MAU) | Day 2 |
| Discord | $0 | Day 1 |
| Canva Pro | $0 (free trial) | Day 1 |
| Instagram/LinkedIn ads (optional) | $50–$100 | Day 6–7 |
| Merch samples (post-launch) | $100–$200 | Week 2+ |
| Contingency | $50–$100 | — |
| TOTAL | $62–$415 |  |

# Post-Launch: Weeks 2–8 Roadmap

The MVP launch is just the beginning. Here’s what to focus on once you have your first members:

## Week 2–3: Validate & Listen

Survey founding members: what do they want most?

Host your first virtual event (workshop, panel, or casual meet).

Identify 2–3 chapter leads from active members.

Launch the merch pre-order page (Printful + Shopify Lite or Gumroad).

## Week 4–5: Build Depth

Add a blog/resources section with student-written content.

Launch the Auevia Chapter Program with a formal application process.

Partner with 1–2 medical student organizations for cross-promotion.

Begin building a mentorship matching feature (even a Google Form MVP works).

## Week 6–8: Scale & Formalize

Incorporate as a nonprofit (if pursuing that route).

Launch the Auevia Certification Program (workshop attendance tracking).

Plan your first in-person or hybrid event.

Explore sponsorship from medical education companies.

Reach 500+ members milestone.

# Success Metrics (Day 7)

| Metric | Target |
| --- | --- |
| Sign-ups | 50+ founding members |
| Discord members | 30+ active in server |
| Social followers | 100+ across Instagram + LinkedIn |
| Chapters seeded | 2–3 founding chapters identified |
| Website uptime | No critical bugs on launch day |
| Engagement | 10+ messages in Discord on day 1 |

Remember: the goal of week 1 isn’t perfection — it’s proof of life. Ship fast, listen to your first members, and iterate. The best version of Auevia will be built by its community, not just its founder.